## Calculator
Risk profile tool
Project name: |  |  | Notes
Use the dropdown menus to select the relevant risks
Project cost | Less than 5% of program budget | 1
| ±25% confidence in cost estimate | 3
| Expected costs are neither allowed for in the annual budget nor externally financed | 5
Project time |  | #N/A
#N/A
#N/A
Project scope |  | #N/A
Project impact |  | #N/A
#N/A
#N/A
#N/A
Project stakeholders |  | #N/A
#N/A
THIS PROJECT IS: | #N/A | #N/A

## Methodology - editable
These tables are editable - you should review them to ensure they meet your project requirements |  | LOW RISK | MEDIUM RISK | HIGH RISK
Settings | Raw score* | 1 | 3 | 5
| Upper limit* | 50% | 75% | 100%
Project cost | 1 | Less than 5% of program budget | Between 5-15% of program budget | Greater than 15% of program budget | 1 | 3 | 5
| 1 | ±10% confidence in cost estimate | ±25% confidence in cost estimate | Greater than 25% margin of error assumed in cost estimate | 1 | 3 | 5
| 1 | Expected costs are fully allowed for in the annual budget or financed by the client | Expected costs are partially allowed for in the annual budget or financed by the client | Expected costs are neither allowed for in the annual budget nor externally financed | 1 | 3 | 5
Project time | 1 | The project can be delivered in less than 3 months | The project can be delivered in less than 6 months | The project will take more than 6 months to deliver | 1 | 3 | 5
| 1 | ±10% confidence in time estimate | ±25% confidence in time estimate | Greater than 25% margin of error assumed in time estimate | 1 | 3 | 5
| 1 | The project has no fixed deadline for delivery | The project has a preferred (but not mandated) delivery window | The project must be delivered on or by a fixed date | 1 | 3 | 5
Project scope | 1 | We have successfully delivered this project five (5) or more times | We have successfully delivered this project at least once before | We have never successfully delivered a project like this | 1 | 3 | 5
Project impact | 1 | Project delivery will noticeably impact one (1) department in our organisation | Project delivery will noticeably impact several departments in our organisation | Project delivery will noticeably impact most or all of our organisation, including core service delivery | 1 | 3 | 5
| 1 | The project has no major precedent or subsequent dependencies | The project has some major precedent or subsequent dependencies | The project has several major precedent or subsequent dependencies | 1 | 3 | 5
| 1 | Project delivery presents no employee or public health and/or safety risks | Employees and/or the public may be at risk of minor injury or illness during project delivery | Employees and/or the public may be at risk of serious injury, illness or loss of life during project delivery | 1 | 3 | 5
| 1 | Project outcomes will fulfil one (1) strategic objective of our organisation | Project outcomes will fulfil several strategic objectives of our organisation | Project outcomes will fulfil most or all of the strategic objectives of our organisation | 1 | 3 | 5
Project stakeholders | 1 | The project can be fully delivered by our current staff | Some project work will need to be shared with proven, existing partners | The project will depend on collaboration with new and/or unknown partners | 1 | 3 | 5
| 1 | The project is only of internal interest to our organisation | There is likely to be some community interest in the project and/or its outcomes | The project and/or its outcomes will be highly visible in the community | 1 | 3 | 5
Definitions | [6 empty] | 65
Raw score | The weighting assigned to a risk. If you want high risks to be more extremely weighted, assign a proportionately higher score to the high risk category.
Upper limit | The point at which a risk converts from low to medium and medium to high. A high score for low and medium means the organisation has a high tolerance for (or willingness to take on) risk. The high risk score is locked at 100%.
This project management template is provided free of charge by the Institute of Project Management under a GNU General Public License.
By downloading and using this resource, you accept its terms and conditions of use.
In short, you can redistribute and/or modify this template to your heart’s content, but without any warranty (real or implied) about its merchantability or fitness for a particular purpose.
This template is offered ‘as is’, and is not supported by a help desk. Please visit http://microsoft.com for editing tips and tricks.
For example, the excel sheets are protected to prevent accidentally overwriting formulas, but not password protected.
You can contact us to learn how this or other project management assets might be customised for your project or organisation.